## CBRE Draw Request Form
CBRE Loan Services
Draw Request Form
Property Name
Draw Number
Last 4 Digits of Bank Acct
Please note: Major and sub-categories (columns F and G) must correspond with the category rows listed on the Capex Tracker sheet. Also, unit numbers listed must be shown on the Interior Unit Tracker sheet and, if applicable, be listed as a full or partial unit renovation If you have any questions regarding completion of this form, please reach out to Bancorpcustomerservice@cbre.com
Type the total $ Invoice / Purchase Order Amount you are requesting in this draw | Invoice Date | Invoice Number | Check # | DROP-DOWN MENU: MAJOR CATEGORY Please enter the category your Invoice / Purchase Order is for: Interior, Exterior, Deferred Maintenance, Immediate Repairs or Contingencies | 'DROP-DOWN MENU: SUB-CATEGORY (LINE ITEM) This is for each Category: Interior, Exterior, Deferred Maintenance, Contingencies | UNIT # Please enter the Unit # where the current invoices / purchase orders / POP correspond to | UNIT TURN TYPE (If applicable) Please indicate if units are a full turn or partial Turn | DROP-DOWN MENU: ELEGIBILITY The Bancorp Allows you to advance: 1) 50% of the contract amount for down payment / deposits of your total Construction Subcontract (subject to submission of conditional lien waiver, Copy of Contract / Invoice, and POP in the next draw); 2) Advances for unpaid Work (subject to submission of conditional lien waiver for invoices in excess of $20k in aggregate per vendor, Copy of Invoice / Purchase Order, and POP in the next draw); 3) Paid Invoices/Purchase Orders with copy of invoices and POP | SUPPORTING INFO FOR ELEGIBILITY: Type the total amount of submitted Construction Subcontract to qualify for the 50% down payment / deposits | SUPPORTING INFO FOR ELEGIBILITY: Name of Sub/Contractor/ or Supplier | DROP-DOWN MENU: SUPPORTING INFO FOR ELEGIBILITY: Mark: Conditional Lien Waiver for: All Deposits/Down payments, Advances, or Invoices that are for $20k in aggregate per Vendor
0 | [5 empty] | Total 50% Construction Subcontract Deposits/Downpayments |  |  | 0

## DO NOT DELETE (hidden)
CATEGORY | LINE ITEMS | ELIGIBILITY FOR DEPOSITS/DOWN PAYMENTS/PAID INVOICES | LIEN WAIVER FOR CONTRACTS > $10K | NEED PROOF OF PAYMENT IN THE NEXT DRAW?
Interior Renovations | Unit upgrades | 1) 50% of the contract amount for Downpayment/Deposits | Conditional Lien Waiver Submitted | POP
Exterior Renovations | Appliances | 2) Advance for Unpaid Work | Conditional Lien Waiver NOT Submitted | n/a
Deferred Maintenance | Flooring | 3) Paid Invoice/Purchase Order
Immediate Reparis | Fixtures
Construction Management Fees | Cabinets
Contingency | washer/dryer machines
New Units
Down Unit
Landscaping
Leasing office
Fitness center
Monument sign
Pool area
Grilling stations
Dog park
EV chargers
Playground
Roofs (seller credit)
Plumbing
Electrical
HVAC
Install and /or repair fencing and gates to comply with security plan.
Repair damaged pavement consisting of linear cracking, alligator cracking, potholes, and surface raveling throughout the Property.
Install security cameras to comply with security plan.
Repair and replace cracked and broken concrete stair treads.
Repair all trip hazards.
Reconfigure the ramp and access walk to provide a level landing at the leasing office entry door
Reconfigure the ADA accessible parking space to provide unobstructed access to aisle.
Interior Contingency
Def. Maintenance Contingency

## CapEx Summary (hidden)
BLUE - Manual Input
BLACK - Formula
Capital Improvement Budget Summary
Category | Total Amount | Per Unit
Interior Renovations | 751200 | 5868.75
Exterior Renovations | 65000 | 507.8125
Deferred Maintenance | 551270 | 4306.7969
Immediate Repairs | 87700 | 685.1562
Construction Management Fees | 0 | 0
Contingency | 36830 | 287.7344
Total Capital Improvement Budget | 1492000 | 11656.25

## CapEx Borrower Budget
BLUE - Manual Input
BLACK - Formula
Borrowing Entity Name: | Red Raider 45 LLC
Property Name: | The Park at Pottsburg Creek
Property Address: | 4800 Atlantic Blvd, Jacksonville, FL 32207
Budget Created By: | Edward Sittler, Vinnie Patel
Date: | 2023-10-13
Total # Units: | 128
# Full Upgrades: | 128
# Partial Upgrades: | 0
Item/Description of Work | # Units | Unit Cost | Total
Interior Budget
Unit upgrades | 0 | 0 | 0
Appliances | 128 | 1500 | 192000
Flooring | 128 | 1500 | 192000
Fixtures | 128 | 1000 | 128000
Cabinets | 128 | 900 | 115200
washer/dryer machines | 128 | 500 | 64000
New Units | 2 | 20000 | 40000
Down Unit | 1 | 20000 | 20000
[Enter] | 0 | 0 | 0
[Enter] | 0 | 0 | 0
[Enter] | 0 | 0 | 0
[Enter] | 0 | 0 | 0
[Enter] | 0 | 0 | 0
[Enter] | 0 | 0 | 0
[Enter] | 0 | 0 | 0
[Enter] | 0 | 0 | 0
[Enter] | 0 | 0 | 0
[Enter] | 0 | 0 | 0
[Enter] | 0 | 0 | 0
[Enter] | 0 | 0 | 0
[Enter] | 0 | 0 | 0
[Enter] | 0 | 0 | 0
[Enter] | 0 | 0 | 0
[Enter] | 0 | 0 | 0
[Enter] | 0 | 0 | 0
Interiors Subtotal |  |  | 751200
Exterior Budget
Landscaping | 1 | 20000 | 20000
Leasing office | 1 | 10000 | 10000
Fitness center | 1 | 5000 | 5000
Monument sign | 1 | 10000 | 10000
Pool area | 1 | 3000 | 3000
Grilling stations | 2 | 2500 | 5000
Dog park | 1 | 5000 | 5000
EV chargers | 2 | 2500 | 5000
Playground | 1 | 2000 | 2000
[Enter] | 0 | 0 | 0
[Enter] | 0 | 0 | 0
[Enter] | 0 | 0 | 0
[Enter] | 0 | 0 | 0
[Enter] | 0 | 0 | 0
[Enter] | 0 | 0 | 0
Exteriors Subtotal |  |  | 65000
Deferred Maintenance
Roofs (seller credit) | 1 | 272000 | 272000
Plumbing | 1 | 179200 | 179200
Electrical | 128 | 440 | 56320
HVAC | 35 | 1250 | 43750
[Enter] | 0 | 0 | 0
[Enter] | 0 | 0 | 0
[Enter] | 0 | 0 | 0
[Enter] | 0 | 0 | 0
[Enter] | 0 | 0 | 0
[Enter] | 0 | 0 | 0
Deferred Maintenance Subtotal |  |  | 551270
Immediate Repairs
Install and /or repair fencing and gates to comply with security plan. | 1 | 30000 | 30000
Repair damaged pavement consisting of linear cracking, alligator cracking, potholes, and surface raveling throughout the Property. | 1 | 28000 | 28000
Install security cameras to comply with security plan. | 1 | 20000 | 20000
Repair and replace cracked and broken concrete stair treads. | 1 | 5000 | 5000
Repair all trip hazards. | 1 | 3000 | 3000
Reconfigure the ramp and access walk to provide a level landing at the leasing office entry door | 1 | 1200 | 1200
Reconfigure the ADA accessible parking space to provide unobstructed access to aisle. | 1 | 500 | 500
[Enter] | 0 | 0 | 0
[Enter] | 0 | 0 | 0
[Enter] | 0 | 0 | 0
Immediate Repairs Subtotal |  |  | 87700
Soft Costs
Interior Contingency |  | 1.704% | 12800
Exterior Contingency |  | 0% | 0
Def. Maintenance Contingency |  | 4.359% | 24030
Construction Management Fees |  | 0% | 0
Soft Costs Subtotal |  |  | 36830
Total CapEx Budget |  |  | 1492000
Escrow Reserves
[Enter] | 0 | 0 | 0
Escrow Reserve Subtoatal |  |  | 1492000
Description/Scope of Work
[Enter any clarifying information here including descriptions of different levels of upgrades if not uniform (e.g., XX units to receive "Elite" upgrades with stainless steel appliances, granite countertops, etc.).]

## CapEx Tracker
BLUE - Manual Input |  |  |  | BLUE - Manual Input
BLACK - Formula |  |  |  | BLACK - Formula
Borrowing Entity Name: | Red Raider 45 LLC
Property Name: | The Park at Pottsburg Creek
Property Address: | 4800 Atlantic Blvd, Jacksonville, FL 32207 |  |  | Property Address: | 4800 Atlantic Blvd, Jacksonville, FL 32207
Budget Created By: | Edward Sittler, Vinnie Patel |  |  | Budget Created By: | Edward Sittler, Vinnie Patel
Date: | 2023-10-13 |  |  | Date: | 2023-10-13
Total # Units: | 128 |  |  | Total # Units: | 128
# Full Upgrades: | 128 |  |  | # Full Upgrades: | 128
# Partial Upgrades: | 0 |  |  | # Partial Upgrades: | 0
Item/Description of Work | # Units | Unit Cost | Total | Item/Description of Work | Original Budget | Budget Reallocations | Adjusted Current Budget | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Total Completed and Stored to date | % Complete | Balance To Finish the Project | Notes
Interior Budget |  |  |  | Interiors | (A) | (B) | (A + B) | (D) | (D) | (D) | (D) | (D) | (D) | (D) | (D) | (D) | (D) | (D) | (D) | (D+D) | (D+D) / (A+B) | (A+B)-(D+D)
Unit upgrades | 0 | 0 | 0 | Unit upgrades | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
Appliances | 128 | 1500 | 192000 | Appliances | 192000 | 0 | 192000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 192000
Flooring | 128 | 1500 | 192000 | Flooring | 192000 | 0 | 192000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 192000
Fixtures | 128 | 1000 | 128000 | Fixtures | 128000 | 0 | 128000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 128000
Cabinets | 128 | 900 | 115200 | Cabinets | 115200 | 0 | 115200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 115200
washer/dryer machines | 128 | 500 | 64000 | washer/dryer machines | 64000 | 0 | 64000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 64000
New Units | 2 | 20000 | 40000 | New Units | 40000 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 40000
Down Unit | 1 | 20000 | 20000 | Down Unit | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 20000
[Enter] | 0 | 0 | 0 | [Enter] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
[Enter] | 0 | 0 | 0 | [Enter] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
[Enter] | 0 | 0 | 0 | [Enter] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
[Enter] | 0 | 0 | 0 | [Enter] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
[Enter] | 0 | 0 | 0 | [Enter] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
[Enter] | 0 | 0 | 0 | [Enter] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
[Enter] | 0 | 0 | 0 | [Enter] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
[Enter] | 0 | 0 | 0 | [Enter] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
[Enter] | 0 | 0 | 0 | [Enter] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
[Enter] | 0 | 0 | 0 | [Enter] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
[Enter] | 0 | 0 | 0 | [Enter] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
[Enter] | 0 | 0 | 0 | [Enter] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
[Enter] | 0 | 0 | 0 | [Enter] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
[Enter] | 0 | 0 | 0 | [Enter] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
[Enter] | 0 | 0 | 0 | [Enter] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
[Enter] | 0 | 0 | 0 | [Enter] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
[Enter] | 0 | 0 | 0 | [Enter] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
Interiors Subtotal |  |  | 751200 | Interiors Subtotal | 751200 | 0 | 751200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 751200
Exterior Budget |  |  |  | Exteriors
Landscaping | 1 | 20000 | 20000 | Landscaping | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 20000
Leasing office | 1 | 10000 | 10000 | Leasing office | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 10000
Fitness center | 1 | 5000 | 5000 | Fitness center | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 5000
Monument sign | 1 | 10000 | 10000 | Monument sign | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 10000
Pool area | 1 | 3000 | 3000 | Pool area | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 3000
Grilling stations | 2 | 2500 | 5000 | Grilling stations | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 5000
Dog park | 1 | 5000 | 5000 | Dog park | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 5000
Playground | 1 | 2000 | 2000 | Playground | 2000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2000
[Enter] | 0 | 0 | 0 | [Enter] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
[Enter] | 0 | 0 | 0 | [Enter] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
[Enter] | 0 | 0 | 0 | [Enter] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
[Enter] | 0 | 0 | 0 | [Enter] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
[Enter] | 0 | 0 | 0 | [Enter] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
[Enter] | 0 | 0 | 0 | [Enter] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
Exteriors Subtotal |  |  | 65000 | Exteriors Subtotal | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 60000
Deferred Maintenance |  |  |  | Deferred Maintenance
Roofs (seller credit) | 1 | 272000 | 272000 | Roofs (seller credit) | 272000 | 0 | 272000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 272000
Plumbing | 1 | 179200 | 179200 | Plumbing | 179200 | 0 | 179200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 179200
Electrical | 128 | 440 | 56320 | Electrical | 56320 | 0 | 56320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 56320
HVAC | 35 | 1250 | 43750 | HVAC | 43750 | 0 | 43750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 43750
[Enter] | 0 | 0 | 0 | [Enter] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
[Enter] | 0 | 0 | 0 | [Enter] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
[Enter] | 0 | 0 | 0 | [Enter] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
[Enter] | 0 | 0 | 0 | [Enter] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
[Enter] | 0 | 0 | 0 | [Enter] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
[Enter] | 0 | 0 | 0 | [Enter] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
Deferred Maintenance Subtotal |  |  | 551270 | Deferred Maintenance Subtotal | 551270 | 0 | 551270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 551270
Immediate Repairs |  |  |  | Immediate Repairs | [18 empty] | # Days to Complete | 2024-01-22
Install and /or repair fencing and gates to comply with security plan. | 1 | 30000 | 30000 | Install and /or repair fencing and gates to comply with security plan. | 30000 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 30000 | 2024-03-31
Repair damaged pavement consisting of linear cracking, alligator cracking, potholes, and surface raveling throughout the Property. | 1 | 28000 | 28000 | Repair damaged pavement consisting of linear cracking, alligator cracking, potholes, and surface raveling throughout the Property. | 28000 | 0 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 28000 | 2024-03-31
Install security cameras to comply with security plan. | 1 | 20000 | 20000 | Install security cameras to comply with security plan. | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 20000 | 2024-03-31
Repair and replace cracked and broken concrete stair treads. | 1 | 5000 | 5000 | Repair and replace cracked and broken concrete stair treads. | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 5000 | 2024-02-29
Repair all trip hazards. | 1 | 3000 | 3000 | Repair all trip hazards. | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 3000 | 2024-02-29
Reconfigure the ramp and access walk to provide a level landing at the leasing office entry door | 1 | 1200 | 1200 | Reconfigure the ramp and access walk to provide a level landing at the leasing office entry door | 1200 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1200 | 2024-02-29
Reconfigure the ADA accessible parking space to provide unobstructed access to aisle. | 1 | 500 | 500 | Reconfigure the ADA accessible parking space to provide unobstructed access to aisle. | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 500 | 2024-02-29
[Enter] | 0 | 0 | 0 | [Enter] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 2024-02-29
[Enter] | 0 | 0 | 0 | [Enter] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 2024-02-29
Immediate Repairs Subtotal |  |  | 87700 | Immediate Repairs Subtotal | 87700 | 0 | 87700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 87700
Soft Costs |  |  |  | Soft Costs
Interior Contingency |  | 1.704% | 12800 | Interior Contingency | 12800 | 0 | 12800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 12800
Exterior Contingency |  | 0% | 0 | Exterior Contingency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
Def. Maintenance Contingency |  | 4.359% | 24030 | Def. Maintenance Contingency | 24030 | 0 | 24030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 24030
Construction Management Fees |  | 0% | 0 | Construction Management Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
Soft Costs Subtotal |  |  | 36830 | Soft Costs Subtotal | 36830 | 0 | 36830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 36830
Total CapEx Budget |  |  | 1492000 | Total Bancorp Funded | 1487000 | 0 | 1487000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1487000
Description/Scope of Work |  |  |  | Deductions |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#VALUE!
|  |  |  | Total Requested |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Escrows (If applicable)
|  |  |  | [Escrow 1] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
|  |  |  | [Escrow 1] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
|  |  |  | [Escrow 1] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
|  |  |  | [Escrow 1] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
|  |  |  | [Escrow 1] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
|  |  |  | Total Bancorp Funded | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0

## Unit Interior Tracker
Borrowing Entity Name
Property Name
Property Address
Date
PLEASE FILL OUT ALL CELLS FOR EACH RENOVATED UNIT AND SUBMIT RENT ROLL
| Ex. 1 bd / 1 bd |  | INCLUDE "X" IF THE UNIT IS RENOVATED AND AVAILABLE FOR LEASING | INCLUDE "X" IF THE UNIT IS NOT FULLY RENOVATED, BUT UNDERGOING RENOVATION | PLEASE FILL OUT DATE THE RENOVATION WAS COMPLETED |  | PLEASE FILL OUT RENT FOR UNIT PRIOR TO RENOVATION | PLEASE FILL OUT RENT UNIT IS LEASE AT. NOT THE MARKET UNIT FOR THE UNIT. LEASE MUST BE SUPPORTED BY RENT ROLL
Unit # | Unit Type | SF | Fully Renovated | Undergoing Renovation | Completion Date of Renovation | Unit Leased? | Prior Leased Rent | New Leased Rent

## Immediate Repairs
Immediate Repairs |  |  | Status
Install and /or repair fencing and gates to comply with security plan. | 1 | 30000
Repair damaged pavement consisting of linear cracking, alligator cracking, potholes, and surface raveling throughout the Property. | 1 | 28000
Install security cameras to comply with security plan. | 1 | 20000
Repair and replace cracked and broken concrete stair treads. | 1 | 5000
Repair all trip hazards. | 1 | 3000
Reconfigure the ramp and access walk to provide a level landing at the leasing office entry door | 1 | 1200
Reconfigure the ADA accessible parking space to provide unobstructed access to aisle. | 1 | 500
[Enter] | 0 | 0
[Enter] | 0 | 0
[Enter] | 0 | 0
Immediate Repairs Subtotal